## Sheet1
JPC-004 | Estimation (hours) | Business Days
|  | D1 | D2 | D3 | D4 | D5 | D6 | D7
Development
JPC-004 Hibernate
DB User and Shema creation | 1 | bar: Business Days D1
DB Scripts pereparation for Table Creation | 2 | Business Days D1: 2
Hibernate Application Skeleton Creation | 2 | Business Days D1: 2
Hibernate configuration for selected DB | 1 | bar: Business Days D1
Configure logging solution | 2 | Business Days D1: 2
Model (Entity) layer implementation | 4 | Business Days D2: 4
Prepare test data | 4 | Business Days D2: 4
Write unit tests | 8 | Business Days D3: 8
DAO layer implementation | 7 | Business Days D4: 7
Service layer implementation | 4 | Business Days D4: 1; Business Days D5: 3
Bug-fixing | 2 | Business Days D5: 2
Code cleanup | bar: Business Days D5
Documents/Testing
Unit testing | 2 | Business Days D5: 2
Configuration Guilde Preparation | 2 | Business Days D6: 2
TOTAL: | 42 | 8 | 8 | 8 | 8 | 8 | 2 | 0